## FP Units (hidden)
FP Units
Function | Complexity | FPs
ILF | Simple | 7
| Avarage | 10
| Complex | 15
EIF | Simple | 5
| Average | 7
| Complex | 10
EI | Simple | 3
| Average | 4
| Complex | 6
EO | Simple | 4
| Average | 5
| Complex | 7
EQ | Simple | 3
| Average | 4
| Complex | 6

## Tittle
Anexo 1: Cajero automatico y gestion de pedidos (CAS LAB04)
COCOMO II Estimation Sheet
1 Document Information
Title | Anexo 1: Cajero automatico y gestion de pedidos |  |  | Version |  | 0.1
Project | Curso Calidad de Software |  |  | Status |  | Draft/Reviewed/Approved
Client | Curso Calidad de Software |  |  | Type |  | Document
Rec # | Christian Raul Mestas Zegarra |  |  | Created |  | 2026-09-28
Author | Christian Raul Mestas Zegarra |  |  | Updated |  | 2026-09-28
1.1 Revision History
Ver. # | Revision Date | Author | Distribution Date |  | Change Ref. | Brief Description
0.1 | 2026-09-28 |  | 2026-09-28
1.2 Distribution List
<DevMgr>
<Company Contact Person>
<Project Team>
1.3 Review and Approvals
Approved By / (Role) |  | Reviewed By / (Role) |  |  |  | Version #

## Introduction
Introduction
TS Cocomo II based estimated sheet is a toolkit for software sizing and estimation. One can estimate the size of work using FP and SLOC. Effort is then estimated using Cocomo II. Effort can then be distributed into different project phases and the project cost is calculated. There is a Rates Sheet for selecting appropriate rate for this specific customer.
FP (Function Points)
Function points are a unit measure for software much like an hour is to measuring time, miles are to measuring distance or Celsius is to measuring temperature
SLOC
Source Line of Code, one line in a computer program. In many languages, each SLOC ends with a semicolon. SLOC is used in COCOMO as the basis for estimating software-development time.
Cocomo II
COCOMO is a model designed by Barry Boehm to give an estimate of the number of programmer-months it will take to develop a software product
How to estimate project size using this toolkit?
Pre-requisite of using this sheet is that user should have familiarity of Function Points (FP). He should be aware of FP counting rules. In the FPs sheet for each feature/component of the application estimate the count and complexity of Internal Logical Files (ILF), External Interface Files (EIF), External Inputs (EI), External Outputs (EO) and External Queries (EQ). There are 3 columns Low, Avg. and High under each category; these columns should have the count of low, average and high complexity components against each application feature. Guidelines on how to judge complexity are provided in comments of ILF, EIF and other headings at the top. Totals are automatically calculated. If there are some features in the applications which doesn't support creation of front-end or maintenance of back-end tables then FP cannot measure its size. Example of such features is any special code libraries that are invoked on schedule or through some other means to do certain functions. For such functions estimate the lines of code in SLOC sheet. Provide feature details, the programming language it will be written in and the estimated LOC count and system will automatically calculate its FPs.
How to estimate effort using this toolkit?
After the FPs and SLOC is estimated go to the effort sheet and estimate the scaling factors and effort multipliers. Guidelines on how to select appropriate value for an effort multiplier or the scaling factor are provided in comments of their respective description. After you have selected the appropriate values please check the consolidated size and effort estimates below. Now the effort is calculated and its time to break this effort into different phases of the project. Please set the percentages in the "Effort Distribution" sheet. Ensure that all percentage should sum to 100%. After setting the percentages please check the effort break-up in the "Effort Summary" sheet.
How to estimate Cost using this toolkit?
After the size and effort are estimated its time to estimate cost. First go to the "Rates" sheet to select primary and secondary rate factors. After selecting the factor check what is the rate tier selected by the system. If "Borderline Case" appear next to the selected rate then you should double check if the selected rate is appropriate. After selecting the rate go to the cost sheet and adjust effort to quote. Round the effort numbers if you feel appropriate. Also check if the blended rate is appropriate and competitive.
How to estimate schedule using this toolkit?
After the cost estimation is complete go to the "Plan sheet" to check if the project can be finished in appropriate duration. Adjust Resources, Slacks and Other Factors and then check if the estimated project duration is appropriate and feasible to the client. If the schedule is not appropriate then re-adjust resources etc to verify if the required project duration can be achieved.

## FPs
|  |  | ILF |  |  | EIF |  |  | EI |  |  | EO |  |  | EQ
Features | Comments | Reference | Low | Avg | High | Low | Avg | High | Low | Avg | High | Low | Avg | High | Low | Avg | High | Total FPs | DEV Days | DEV Hours | Total Days
Anexo 1 Parte A: cajero automatico (retiro, deposito, transferencia y consultas) | 3 ILF, 2 EIF, 4 EI, 2 EO y 2 EQ de la Parte A; 76 PF |  | 0 | 3 | 0 | 0 | 2 | 0 | 0 | 4 | 0 | 0 | 2 | 0 | 2 | 0 | 0
Anexo 1 Parte B: gestion de pedidos (clientes, cuentas, productos y cobro) | 3 ILF, 5 EI, 2 EO y 1 EQ de la Parte B; 63 PF |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 2 | 0 | 1 | 0 | 0
Total Anexo 1 (Parte A + Parte B)
Total FP
Note on E2: ILF Complexity: RETs 1-19 DETs 20-51 DETs 51+ DETs ---- --------- ---------- -------- 1 Low Low Avg 2-5 Low Avg High 6+ Avg High High
Note on H2: EIF Complexity: RETs 1-19 DETs 20-51 DETs 51+ DETs ---- --------- ---------- -------- 1 Low Low Avg 2-5 Low Avg High 6+ Avg High High
Note on K2: EI Complexity: FTRs 1-4 DETs 5-15 DETs 16+ DETs ---- -------- --------- -------- 0-1 Low Low Avg 2 Low Avg High 3+ Avg High High
Note on N2: EO Complexity: FTRs 1-5 DETs 6-19 DETs 20+ DETs ---- --------- --------- -------- 0-1 Low Low Avg 2-3 Low Avg High 4+ Avg High High
Note on Q2: EQ Complexity: FTRs 1-5 DETs 6-19 DETs 20+ DETs ---- --------- --------- -------- 0-1 Low Low Avg 2-3 Low Avg High 4+ Avg High High

## SLOC
Features | Comments | Reference | Language | Estimated SLOC | Total FPs | Dev Days | Total Days
Sin SLOC directo: tamano derivado de puntos de funcion del Anexo 1 |  |  | Java,JSP,J2EE | 0
Total:

## Backfiring (hidden)
Language/Technology | SLOC
C++ | 60
C# | 59
Java,JSP,J2EE | 60 | Average of three
Excel | 47
JavaScript | 56
HTML | 43
Visual Basic | 50
PLSQL/SQL | 42 | Average of both
VB Script | 45
NOTE: Above Numbers are Taken from http://www.qsm.com/FPGearing.html. Average values are taken

## Effort
Cocomo II
PM = A*Size^E*Product(All Effort Multipliers - EM)
Exponent E = B+(0.01*SUM(Scaling Factors))
Scaling Factors
SF | Description | Level | Value | Instructions/Comments
Maturity | Process Maturity | Nominal |  | Recommended values for CMMi level 2 companies is Nominal. For Level 3 its High
PREC | Experience of similar Projects | Low |  | For Projects of new domain (that is domain we have not worked on) always select low. Select Nominal or High for projects that we are creating from scratch but we have some knowledge about domain. Select very high or extremely high for Next Releases of existing projects
FLEX | Flexibility required in the System | Nominal |  | We usually use Nominal but check comments on description for details
TEAM | Team Cohesiveness | High |  | Team Cohesiveness is always extremely high in projects where team is small and not distributed across the globe
RESL | Project Risk and Architectural Complexity | Nominal |  | We usually use Nominal but check comments on description for details
Effort Multiplier EM
EM | Description | Level | Value | Instructions/Comments
RCPX | System reliability, complexity and size indicator | Very Low |  | The kind of projects we have in Technosoft we normally use extra low or very low. Check comments on description for details
RUSE | Reusability concern with respect to current and future projects | Low |  | We usually use Low but check comments on description for details
PDIF | Platform Difficulty | Very Low |  | We usually use Very Low but check comments on description for details
PERS | Personal capability of team. Like technical capability of Programmers, Designers and testers. | High |  | We usually use High but check comments on description for details
PREX | Application, Language and tool experience | High |  | We usually use High but check comments on description for details
FCIL | Using Case tools for development etc | High |  | We usually use High for .NET and Nominal for java but check comments on description for details
SCED | Schedule Pressure | Nominal |  | We usually use Nominal but check comments on description for details
Constants | Value
B | 0.91
B2 | 1.23
A | 2.94
E
EM
Consolidated Size and Effort
Technology | Java,JSP,J2EE
Increase due to lifecycle | 0%
SLOC per FP
SLOC
PM
Man-days
FP from LOC
Hours per FP |  | Usually this number should be between 6 to 10 hours depending upon above parameters
SF Scale | PREC | FLEX | TEAM | RESL | Maturity
Very Low | 6.2 | 0 | 5.48 | 0 | 7.8
Low | 4.96 | 1.01 | 4.38 | 1.41 | 6.24
Nominal | 3.72 | 2.03 | 3.29 | 2.83 | 4.68
High | 2.48 | 3.04 | 2.19 | 4.24 | 3.12
Very High | 1.24 | 4.05 | 1.1 | 5.65 | 1.56
Extremely High | 0 | 5.07 | 0 | 7.07 | 0
EM Scale | RCPX | RUSE | PDIF | PERS | PREX | FCIL | SCED
Extra Low | 0.49 | 0.95 | 0.87 | 2.12 | 1.59 | 1.43 | 1
Very Low | 0.6 | 0.95 | 0.87 | 1.62 | 1.33 | 1.3 | 1
Low | 0.83 | 0.95 | 0.87 | 1.26 | 1.22 | 1.1 | 1
Nominal | 1 | 1 | 1 | 1 | 1 | 1 | 1
High | 1.33 | 1.07 | 1.29 | 0.83 | 0.87 | 0.87 | 1.14
Very High | 1.91 | 1.15 | 1.81 | 0.63 | 0.74 | 0.73 | 1.43
Extremely High | 2.72 | 1.24 | 2.61 | 0.5 | 0.62 | 0.62 | 1.43
Note on C9: Very Low/Low: - Little to moderate experience of working with similar projects. - Moderate understanding of project objectives and business needs - Extensive need for new Operational process or Hardware. Nominal/High: - Considerable experience of working with similar projects. - Considerable understanding of project objectives and business needs - Moderate need for new Operational process or Hardware. Very High/Extra High: - Extensive experience of working with similar projects. - Thorough understanding of project objectives and business needs - Little or no need for new Operational process or Hardware.
Note on C10: Very Low/Low: - Full compliance with pre-established requirements - Full compliance with External Interface Specifications Nominal/Very High: - Considerable with pre-established requirements - Considerable with External Interface Specifications Very High/Extra High: - Basic compliance with pre-established requirements - Basic compliance with External Interface Specifications
Note on C12: Very Low/Low: - Little or no Risk Management is required for the project - Simple Architecture requiring less time in Design Nominal/Very High: - Considerable Risk Management is required for the project - Moderately Complex Architecture requiring more time in Design and requires some usage of latest frameworks Very High/Extra High: - Extensive Risk Management is required for the project - Complex Architecture requiring a lot of time in Design and requires use of latest frameworks
Note on C16: Extra Low: - Easily recoverable losses in case of system failure - Very low documentation needs - Very Simple code with low algorithmic complexity - Project size is 0 to 200 FP Very Low/Low: - Slight inconvenience or easily recoverable losses in case of system failure - Very low to low documentation needs - Simple code with low algorithmic complexity - 200<FP<1000, less than 500 fp is very low Nominal: - Moderate inconvenience or recoverable losses in case of system failure - Normal documentation needs i.e. creation routine documents for different life-cycle phases - Moderately complex code. May have IO Processing, Nested logical structures stc. - 1000<FP<5000 High: - High financial losses in case of system failure - Excessive documentation required - Complex code. Having complex nested logic, Encryption-Decryption or other complex code structures. - 5000<FP<10000 Very High: - Risk to human life in case of system failure - Very Excessive documentation required - Very Complex code. Having complex nested logic, Encryption-Decryption or other complex code structures. - 10000<FP
Note on C17: Extra Low/Very Low/Low: - No Reusability requirements Nominal: - Reusable components need to be created within the scope of the application i.e. certain reusable components need to be created which will be used by all other modules within this application High/Very High: - Reusable components need to be created within for multiple application within a suite of applications Extra High: - Reusable components need to be created for all application. These components might need to be designed like services using SOA or web services concepts.
Note on C18: NOTE: Measure on DEV and Internal Test Platform Extra Low/Very Low/Low: - Major Changes every 12 month - Minor Changes every month Nominal: - Major Changes every 6 month - Minor Changes every 2 week High: - Major Changes every 2 month - Minor Changes every 1 week Very High/Extra High: - Major Changes every 2 month - Minor Changes every 2 days
Note on C19: NOTE: Calculate team proficiency in percentage using the following guideline and than calculate rating. Experience > 5 year = 100% Experience > 3 year = 90% Experience > 2 year = 80% Experience > 1 year = 70% Experience > 9 month = 60% Experience > 6 month = 50% Experience > 3 month = 40% Experience < 3 month = 25% Extra Low < 35% Very Low >= 35% Low>= 45% Nominal >= 55% High >= 65% Very High >= 75% Extra High >= 85%
Note on C20: NOTE: Count experience with similar technology, language and tool. Take teams Average Experience Extra Low - Less than 3 month Very Low - More than 3 month Low: - More than 6 month Nominal: - More than 9 month High: - More than 1 year Very High - More than 2 year Extra High: - More than 3 year
Note on C21: Extra Low: - No tools IDEs and related tools are available for supporting development Very Low: - IDEs are being used to support front-end and back-end development. Low: - Some already developed supporting frameworks are available to help develop few things quickly e.g. struts Nominal: - Tools are available that generate code to a certain extent but that code then needs to further worked on a lot before it goes to development. Wise wig and related drap-drop event based developed which provides widgets tools etc. fall in this category High/Very High/Extra High: - Tools generate code to a greater extent
Note on C22: Extra Low/Very Low/Low/Nominal: - Reasonable time is allocated to project and there no or little schedule pressure High: - Project has to finished in 85% time of normal schedule Very High/Extra High: - Project has to finished in 75% time of normal schedule

## Effort Distribution
Summary Units
Category | Percentage of Development
Requirements Analysis | 7%
Architecture & Design | 7%
Development | 38%
Customer Review Changes | 10%
Test Planning | 4%
Testing | 10%
Bug Fixes | 10%
Documentation | 0%
Training | 0%
Deployment | 2%
Project Planning | 2%
Project Monitoring | 6%
CM | 2%
Audits | 2%
NOTE: Above numbers are estimated distribution on the basis of experience and on the basis of previous projects

## Effort Summary
Category | Effort (Days) | Effort (Hours) | Comments/Assumptions
Requirements Analysis Hours
Architecture, FS and A&D Hours
Output are Test Plan and Test Cases
Output is Test Results
Outputs are Deployment and Build Documents
Effort to deploy application
Total Effort

## Cost
Cost Units
Units | per hour | per days
Analista | 9.4
Desarrollador | 9.4
Probador | 9.4
Documentador | 7.5
Jefe de proyecto | 11.3
Soporte | 5.6
On-site Manager | 0
Discount | Percentage: | Comments (Reason for Discount):
Discount by Dev Team: | 0% | Sin descuento de equipo: trabajo academico
Discount by Sales Team: | 0% | Sin descuento comercial: trabajo academico
Total Discount:
Total Project Cost
Category | Effort (Days) Estimated | Discounted Effort for Sales | Rounded Effort | Effort (Hours) | Cost
Total
Blended Rate
Effort and Cost to Quote
Category | Effort (Days) | Effort (Hours) | Cost
Analysis and Design
Test Planning
Testing
Defect Fixation during Internal Testing
User Manuals and Install Guides
Training
Deployment
Project Management
Total
Total Support Cost
Man Months | 1
Man Days | 5
Category | Hours per day | Total Hours |  | Cost
Designers | 0.5
Developers | 8
Testers | 1
Managers | 0.5
Total

## Plan 1
Assumptions
Test Planning, Documentation and Management activities are carried out in parallel to other main activities of design, development and testing
Resources |  |  | Slacks
Designers | 1 |  | Initial Ramp-up | 1
Developers | 1 |  | Deployment for testing etc | 1
Testers | 1 |  | Code/Peer Reviews | 1
Others |  |  | Shipment Packaging & Review | 1
Comunication Delay in Analysis and Design | 25% |  | Total Slack
Possible Critical Chain Delay in Development | 15%
Possible Fixation Delay in Testing | 20%
Working days in a month | 21
Ratio of calendar days
Project Plan - Waterfall
Phase | Duration (days) | Duration (months)
Requirements/Design Phase
Development Phase
Testing Phase
Total
Slack
Grand Total
Iterative Plan
Iterations | 2 | Iteration Duration (without Slacks) | Requirements/Design | Development | Testing
1
2
3
4
5
Total

## Plan 2
Assumptions
Test Planning, Documentation and Management activities are carried out in parallel to other main activities of design, development and testing
Resources |  |  | Slacks
Business Analyst | 1 |  | Initial Ramp-up | 1
Architects & Designers | 1 |  | Deployment for testing etc | 1
Developers | 1 |  | Code/Peer Reviews | 1
Testers | 1 |  | Shipment Packaging & Review | 1
Others |  |  | Total Slack
Comunication Delay in Analysis and Design | 25%
Possible Critical Chain Delay in Development | 15%
Possible Fixation Delay in Testing | 20%
Working days in a month | 21
Ratio of calendar days
Project Plan - Waterfall
Phase | Duration (days) | Duration (months)
Requirements Analysis
Design Phase
Development Phase
Testing Phase
Total
Slack
Grand Total
Iterative Plan
Iterations | 3 | Iteration Duration (without Slacks) | Comments
1 | 20% |  | Includes A&D Phase plus percentage of Development Phase
2 | 50% |  | Percentage of development phase
3 | 30% |  | Percentage of development phase and testing
4
5
Total